Phase 1 Engineering Plan

Flow OS — Companion Document #3

Month-by-Month Task Breakdown (Months 1-2: Foundation)

Version 1.0  |  April 2026

# 1. How to Use This Document

This is an actionable week-by-week plan for Phase 1 of Flow OS (Foundation, Months 1-2). It exists because a 7-month roadmap is not something you can execute from; you execute from a week.

The plan assumes a solo developer working roughly 40 focused hours per week. If you're building this part-time (20 hours/week), double the timeline. If you're sprinting full-time plus evenings (60 hours/week), you may beat it by 20%. Honest estimation matters more than optimistic estimation.

## 1.1 Operating Principles

- One thing at a time: Finish a task before starting the next. Half-finished work is technical debt.

- Deploy continuously: Staging environment live from day 3. Prod-like from week 2.

- Commit often: Small PRs even as a solo dev. Force yourself to write clear commit messages — they become your memory.

- Weekly self-review Friday afternoon: What shipped? What slipped? What changes?

- Build in public: Post progress on Twitter/LinkedIn at minimum weekly. Accountability plus marketing.

## 1.2 What Phase 1 Delivers

At the end of Month 2, you will have:

- Deployed staging environment for apps/web (authenticated workspace app)

- Working auth with email/password + Google OAuth

- Multi-workspace support with membership/roles

- Turborepo monorepo with 8+ internal packages, CI-enforced boundaries

- BlockNote editor integrated with real-time collaboration via Hocuspocus

- Page tree navigation, command palette, search

- Basic database abstraction with Table view

- Clean codebase you can confidently extend through Phase 2

Phase 1 does NOT deliver any business features (clients, time, invoices, agents). That's Phase 2-4. Resist scope creep.

## 1.3 What Phase 1 Is Not

- Not a product users will pay for. Only you are running this at end of Month 2.

- Not polished. Design polish is deferred. Functional is enough.

- Not feature-complete. It is the foundation; you will delete scaffolding later, and that's fine.

# 2. Pre-Kickoff (Week 0)

Before writing any code, do these five things. Two days, total.

## 2.1 Decide the Open Questions

From PRD Section 12, make firm decisions on:

- Product name and domain (you can refine later, but stop working with placeholders)

- License (AGPL vs MIT; leaning AGPL per PRD)

- Hosting accounts you'll need (Vercel, Supabase, Stripe, Resend, Anthropic API)

## 2.2 Set Up Accounts and Secrets

- GitHub organization or personal account

- Vercel account with team set up

- Supabase account with two projects: dev and staging

- Stripe test mode account

- Resend account with verified sending domain

- Anthropic console + API key (dev budget: $50/month cap)

- Domain registered; Cloudflare for DNS

- Password manager: store all keys in 1Password or Bitwarden

## 2.3 Local Development Setup

- Node 22 LTS, pnpm 9+, Docker Desktop

- VS Code or Cursor with TypeScript, ESLint, Prettier extensions

- Git with signed commits configured

- Supabase CLI for local dev

- Postgres client (Postico or TablePlus)

## 2.4 Create Work Tracking

Do not use Flow OS for this (you haven't built it yet, and dogfooding a work-in-progress tool on critical work is a bad idea). Use whatever you're fastest in: Linear, a markdown file in the repo, or even a paper notebook. The goal is to offload open loops from your brain.

- Issue/todo tracker with this doc's tasks broken into tickets

- A "decisions log" markdown file in the repo for architectural decisions

- A "learnings" markdown file for gotchas you discover

## 2.5 Block Time

Calendar block for deep work. Solo founder's biggest enemy is fragmented time. Recommendation: 2 blocks of 3 hours per day, morning and afternoon, protected from meetings and Slack. Everything else fits around those blocks.

# 3. Month 1: Infrastructure and Auth

## 3.1 Week 1: Monorepo and CI

### Goals

- Turborepo scaffolded with package structure matching PRD Section 6.7

- ESLint and dependency-cruiser rules enforcing boundaries

- GitHub Actions CI running on every push

- Vercel deployment for apps/web (placeholder page)

### Tasks

| Day | Task | Deliverable |
| --- | --- | --- |
| Mon | pnpm init, Turborepo setup, tsconfig, eslint, prettier base config | Empty monorepo builds clean |
| Tue | Create apps/web (Next.js 15), apps/portal, apps/docs (placeholders) | 3 apps build |
| Wed | Create packages: db, auth, ui, config (shared tsconfig/eslint/tailwind) | Packages resolve and import |
| Thu | GitHub Actions: lint, typecheck, build on PR. Dependency-cruiser rules | CI green on main |
| Fri | Vercel deploy apps/web to staging, custom domain | Staging URL live |

### Concrete package.json structure

// packages/config/package.json

{

"name": "@flow/config",

"version": "0.0.1",

"private": true,

"main": "./index.ts",

"exports": {

"./eslint": "./eslint.config.js",

"./tsconfig": "./tsconfig.base.json",

"./tailwind": "./tailwind.config.ts"

}

}

### Dependency-cruiser rule example

// .dependency-cruiser.cjs

module.exports = {

forbidden: [

{

name: 'no-cross-domain-imports',

severity: 'error',

from: { path: '^packages/(clients|projects|time|invoicing)' },

to:   { path: '^packages/(clients|projects|time|invoicing)',

pathNot: '\\$1' }

},

{

name: 'no-service-to-app',

severity: 'error',

from: { path: '^services' },

to: { path: '^apps' }

}

]

};

### Definition of Done

- Pushing to main deploys apps/web to Vercel staging within 3 minutes

- Creating a PR runs lint, typecheck, build, dependency-cruiser automatically

- Attempting to import from @flow/projects inside @flow/clients fails CI

- README documents setup steps sufficient for you to rebuild from scratch in 30 minutes

## 3.2 Week 2: Database and Auth

### Goals

- Supabase project connected; Drizzle ORM set up in packages/db

- Initial schema: users, workspaces, memberships (with RLS policies)

- Auth flow: signup, login, logout via Supabase Auth

- Google OAuth working

### Tasks

| Day | Task | Deliverable |
| --- | --- | --- |
| Mon | Supabase project setup, Drizzle config, connection pooling | Drizzle can query Supabase |
| Tue | Schema: users, workspaces, memberships. Drizzle migrations | Tables created in dev DB |
| Wed | RLS policies for workspace isolation. Test with two test users | User A can't read User B's data |
| Thu | apps/web auth pages: signup, login, forgot password. Supabase SSR | Can sign up and log in |
| Fri | Google OAuth provider configured; test complete flow | Can log in with Google |

### Schema for Week 2

-- packages/db/schema/auth.ts reflects these tables

CREATE TABLE users (

id UUID PRIMARY KEY REFERENCES auth.users(id),

email TEXT NOT NULL UNIQUE,

name TEXT,

avatar_url TEXT,

timezone TEXT DEFAULT 'UTC',

created_at TIMESTAMPTZ DEFAULT NOW()

);

CREATE TABLE workspaces (

id UUID PRIMARY KEY DEFAULT gen_random_uuid(),

slug TEXT NOT NULL UNIQUE,

name TEXT NOT NULL,

plan TEXT NOT NULL DEFAULT 'free',

settings JSONB NOT NULL DEFAULT '{}',

created_at TIMESTAMPTZ DEFAULT NOW()

);

CREATE TYPE membership_role AS ENUM ('owner','admin','member','guest');

CREATE TABLE memberships (

workspace_id UUID NOT NULL REFERENCES workspaces(id) ON DELETE CASCADE,

user_id UUID NOT NULL REFERENCES users(id) ON DELETE CASCADE,

role membership_role NOT NULL DEFAULT 'member',

created_at TIMESTAMPTZ DEFAULT NOW(),

PRIMARY KEY (workspace_id, user_id)

);

### RLS Policy Example

-- Workspaces: users can only see workspaces they're a member of

CREATE POLICY workspace_member_read ON workspaces

FOR SELECT USING (

id IN (SELECT workspace_id FROM memberships

WHERE user_id = auth.uid())

);

### Definition of Done

- Two separate user accounts cannot see each other's data

- Google OAuth logs users in correctly

- Logout works cleanly; protected routes redirect to login

- All auth flows work on mobile web

## 3.3 Week 3: Workspace Creation and Onboarding

### Goals

- New user is walked into creating their first workspace

- Workspace switcher in sidebar

- Invite teammates via email with role selection

- Settings page: workspace details, members list, plan (placeholder)

### Tasks

| Day | Task | Deliverable |
| --- | --- | --- |
| Mon | Post-signup flow: create workspace with auto-generated slug | New user creates workspace |
| Tue | Workspace switcher UI in top of sidebar | Can switch between 2 workspaces |
| Wed | Invite teammate flow: email form, generates invite token, Resend email | Invite received in inbox |
| Thu | Accept-invite page; auto-add to workspace on signup or login | Teammate joins successfully |
| Fri | Settings page: workspace details edit, members list, remove member | Admin can manage members |

### Definition of Done

- New user goes from signup to having an empty workspace in under 60 seconds

- Inviting a teammate sends them a working magic link

- Workspace admin can remove a member and that member loses access immediately

- Non-admin members cannot access settings page

## 3.4 Week 4: Shell UI and Navigation

### Goals

- Sidebar navigation with pages section (placeholder), workspace switcher, user menu

- Command palette (Cmd+K) with keyboard-first navigation

- shadcn/ui base components wired up in packages/ui

- Dark mode toggle, responsive shell

### Tasks

| Day | Task | Deliverable |
| --- | --- | --- |
| Mon | Install shadcn/ui components; set up Tailwind config in packages/ui | Button, Input, Dialog usable |
| Tue | Build AppShell with sidebar, topbar, main content area | Shell renders on all routes |
| Wed | Command palette: cmdk library, empty categories (Navigate, Actions) | Cmd+K opens palette |
| Thu | User menu (avatar dropdown), workspace switcher, settings links | Full nav works |
| Fri | Dark mode (next-themes), responsive breakpoints, mobile sidebar drawer | Works on mobile and desktop |

### Definition of Done

- Shell is pixel-clean, not polished but not ugly

- Keyboard navigation works: Tab through all interactive elements

- Cmd+K opens palette from anywhere

- Mobile: sidebar slides in; all main elements fit under 375px

- No console warnings in production build

# 4. Month 2: Pages, Editor, and Databases

## 4.1 Week 5: Page Tree and Basic CRUD

### Goals

- Pages can be created, renamed, deleted, and nested in a tree

- Page list in sidebar with expand/collapse

- Drag to reorder, drag to nest

- Page URLs: /w/{workspace-slug}/p/{page-id}

### Tasks

| Day | Task | Deliverable |
| --- | --- | --- |
| Mon | Pages schema: id, workspace_id, parent_id, title, icon, order, created_by | Migration applied |
| Tue | Create/rename/delete pages (server actions). Basic tree query | Can create a page |
| Wed | Sidebar tree component: nested rendering, expand/collapse | Tree renders correctly |
| Thu | Drag-and-drop reordering using dnd-kit | Can reorder and nest |
| Fri | Page URLs with dynamic routes; breadcrumb nav at top of page view | Deep links work |

### Definition of Done

- Can create 20 nested pages and UI stays responsive

- Reordering persists across reloads

- Deleting a page with children prompts for confirmation and handles recursively

- Breadcrumbs show correct path

## 4.2 Week 6: BlockNote Editor Integration

### Goals

- BlockNote editor rendering on every page

- Content persists to Postgres as JSON on change (debounced)

- Slash menu works; default blocks functional

- Image upload to Supabase Storage

### Tasks

| Day | Task | Deliverable |
| --- | --- | --- |
| Mon | packages/editor: wrap BlockNote, expose typed API. Add to page view | Editor renders |
| Tue | Save on debounce (500ms) via server action. Optimistic state | Content persists |
| Wed | Slash menu with all default blocks (text, headings, lists, code, quote) | Slash menu works |
| Thu | Image upload: presigned URL to Supabase Storage; paste + drag support | Images upload and render |
| Fri | File attachment block; video embed block; link preview block | Additional blocks work |

### Definition of Done

- Can type a long page with headings, lists, images; reload; everything persists

- Paste-from-Notion works reasonably (BlockNote handles most formatting)

- Image upload limit enforced (10MB)

- No data loss on quick reload after edit

## 4.3 Week 7: Real-Time Collaboration

### Goals

- Hocuspocus Yjs server deployed to Railway

- Two users editing same page see each other's changes live

- Cursors and selection awareness shown

- Page persists even when no user is connected

### Tasks

| Day | Task | Deliverable |
| --- | --- | --- |
| Mon | services/realtime: Hocuspocus setup with Supabase persistence adapter | Server running locally |
| Tue | Deploy Hocuspocus to Railway. Configure WebSocket URL env var | Server reachable from app |
| Wed | Client-side Yjs provider in editor package. Auth via token | One user can edit collaboratively |
| Thu | Presence: avatars of connected users, cursor positions | Presence shows live |
| Fri | Persistence: ensure doc saved to DB when last user disconnects | Content persists between sessions |

### Definition of Done

- Two tabs editing same page sync within 300ms

- Disconnecting and reconnecting does not lose changes

- Other users' cursors visible with their name

- WebSocket auth prevents cross-workspace access

### Known Risk

Real-time is the riskiest week in Month 2. If Hocuspocus setup on Railway takes longer than expected (likely — WebSocket deployments have quirks), budget to slip Week 7 by 2-3 days and cut Week 8 scope accordingly. Real-time is important but the foundation must ship on time.

## 4.4 Week 8: Basic Database and Table View

### Goals

- Generic database abstraction: create a "database" with columns and rows

- Table view with sortable columns, inline edit, add/remove rows

- Support property types: text, number, select, checkbox, date

- Foundation that the business entities (Clients, Projects) will sit on top of in Phase 2

### Tasks

| Day | Task | Deliverable |
| --- | --- | --- |
| Mon | Schema: databases, database_columns, database_rows (JSONB properties) | Migration applied |
| Tue | Create database, add/remove columns, edit column type | DB definition works |
| Wed | Table view component: headers, rows, inline editing for text/number | Can edit cells |
| Thu | Select property (color-coded tags), checkbox, date picker | All property types work |
| Fri | Sort, filter (simple), column resize. Persistence of view config | Table is usable |

### Definition of Done

- Can create a "Tasks" database with 5 columns, add 20 rows, edit cells

- Sorting and filtering work, state persists

- Inline cell editing saves within 500ms of blur

- Works on mobile (scrollable table)

# 5. End of Phase 1 Review

## 5.1 Demo Checklist

At end of Week 8, record a 5-minute video demonstrating:

- Signup flow (email and Google)

- Creating a workspace, inviting a teammate

- Creating nested pages with the editor

- Two browsers editing same page with live presence

- Creating a database, adding rows, sorting

Post this video in your build-in-public channel. It's proof the foundation works and generates waitlist interest.

## 5.2 Technical Health Check

- CI build time under 3 minutes

- Staging deploy time under 5 minutes

- Zero dependency-cruiser violations

- TypeScript strict mode enabled everywhere; no 'any' leaks

- Test coverage on critical paths: auth, workspace creation, editor persistence

- No security issues from Snyk or npm audit (critical/high)

## 5.3 Retrospective Questions

Friday of Week 8, answer honestly:

- Which weeks slipped and why? Are those root causes addressed?

- What tech choice do you now regret? (If anything — better to catch early.)

- Are you burning out? If yes, recalibrate Phase 2 timeline.

- Is the codebase still a place you're excited to open? (If not — urgent; clean up before Phase 2.)

- Have you talked to any real VAs yet? (If not, schedule 3 calls in Week 9.)

## 5.4 Decision Point

End of Phase 1 is the last good moment to pivot. If the foundation is solid and you're energized, Phase 2 (business core) is mechanical. If you're struggling technically or motivationally, honest options:

- Narrow scope: drop Agent #4 from v1, simplifying the mesh

- Extend timeline: accept 9 months instead of 7

- Find a collaborator: designer or contractor to handle 20-30% of load

- Pivot: if you've learned the market is different than you thought, better to change now than after 5 more months

# 6. Complete Phase 1 Task List

Every task from the 8 weeks, consolidated:

## 6.1 Week 1 — Monorepo

- Initialize pnpm + Turborepo monorepo

- Create apps/web, apps/portal, apps/docs (Next.js 15)

- Create packages: db, auth, ui, config

- Configure shared tsconfig, eslint, prettier, tailwind

- Set up GitHub Actions CI (lint, typecheck, build, dep-cruiser)

- Vercel deployment for apps/web to staging

- Configure custom domain for staging

## 6.2 Week 2 — Database and Auth

- Supabase projects (dev, staging)

- Drizzle ORM setup in packages/db

- Schema: users, workspaces, memberships

- RLS policies for workspace isolation

- Supabase Auth integration with Next.js SSR

- Signup, login, logout, forgot password pages

- Google OAuth provider

- Protected route middleware

## 6.3 Week 3 — Workspaces

- Post-signup workspace creation flow

- Workspace slug generation and validation

- Workspace switcher UI

- Invite teammate via email + token

- Resend integration for invite emails

- Accept invite flow (new user + existing user)

- Settings page with workspace details

- Members list with add/remove/change role

- Role-based access (owner/admin/member/guest)

## 6.4 Week 4 — Shell UI

- Install and configure shadcn/ui in packages/ui

- AppShell component (sidebar + main)

- Sidebar with sections: pages, clients (placeholder), etc

- Command palette with cmdk

- Navigate commands in palette

- User avatar menu

- Dark mode toggle via next-themes

- Mobile: responsive sidebar drawer

## 6.5 Week 5 — Pages

- Pages schema + migration

- Server actions for create/rename/delete/move

- Tree query with recursive CTE

- Sidebar page tree with expand/collapse

- Page icons (emoji picker)

- Drag-and-drop reordering (dnd-kit)

- Drag to nest into parent

- Dynamic page URLs with breadcrumbs

- Delete confirmation with child handling

## 6.6 Week 6 — Editor

- packages/editor: BlockNote wrapper

- Editor renders on every page

- Debounced content save (JSON to Postgres)

- Optimistic UI with rollback on failure

- Slash menu with all default blocks

- Image upload to Supabase Storage

- File attachment block

- Video embed block

- Link preview block

## 6.7 Week 7 — Real-Time

- services/realtime: Hocuspocus server

- Supabase persistence adapter

- Deploy to Railway with WebSocket support

- Client-side Yjs provider in editor

- Auth token for WebSocket connection

- Presence awareness (connected users)

- Cursor and selection display

- Reconnection handling

- Persistence on last-user-disconnect

## 6.8 Week 8 — Databases

- Schema: databases, database_columns, database_rows

- Database definition UI: add/remove columns

- Property types: text, number, select, checkbox, date

- Table view component

- Inline cell editing

- Column sort

- Simple filters

- Column resize and reorder

- View config persistence

# 7. Phase 1 Risks and Mitigations

## 7.1 Technical Risks

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Hocuspocus deployment issues on Railway | Medium | Budget slack in Week 7; fall back to Fly.io if Railway flaky |
| Supabase RLS complexity blocking progress | Medium | Start with simple policies; iterate; test with two user fixture early |
| BlockNote customization limitations discovered | Low-Med | Validate custom blocks work in Week 6 spike; Plate.js is backup |
| Dependency-cruiser rules too strict, blocking velocity | Low | Rules are adjustable; err toward permissive early, tighten later |
| Yjs persistence inconsistencies | Low | Battle-tested; follow Hocuspocus docs exactly |

## 7.2 Personal Risks

- Burnout: 8 weeks of intense focus is sustainable; 16 weeks is not without real breaks. Take a full weekend off every 4 weeks minimum.

- Isolation: Solo dev is lonely. Schedule 2 calls/week with other founders or friends — this is not optional.

- Scope creep: "Wouldn't it be cool if..." is how weeks slip. Keep a "later" list; move ideas there, do not build them.

- Tech rabbit holes: If stuck on a technical problem for more than 4 hours, stop. Rubber duck, sleep on it, ask online. Grinding rarely helps.

## 7.3 Market Risks During Phase 1

Phase 1 is invisible to the market — you're not shipping anything users see. But this is the period when you should:

- Interview 10-15 real VAs about their current tooling (validate the problem)

- Build waitlist through build-in-public content (validate demand)

- Watch competitors: subscribe to Notion/ClickUp/Dubsado newsletters for feature signals

- If a competitor ships something that kills your differentiation during Phase 1 — address it now, not at launch

# 8. Phase 2 Preview (for Context)

Phase 1 must end clean because Phase 2 builds heavily on it. Here's what comes next so you can make Phase 1 decisions with Phase 2 in mind:

## 8.1 Phase 2: Business Core (Weeks 9-16)

- Week 9-10: packages/clients, packages/projects, packages/time. Client and Contact entities with dedicated UIs.

- Week 11-12: Time tracking (sidebar timer, manual entry, timesheets). This is where your database abstraction from Week 8 gets stress-tested.

- Week 13-14: Invoicing (generation, PDF, email).

- Week 15: Stripe subscriptions for Flow OS itself.

- Week 16: Board view, calendar view, dogfood your own use of the product.

## 8.2 Phase 2 Implications for Phase 1

- The Pages abstraction from Week 5 must support embedding database views — design tree structure accordingly

- The database abstraction from Week 8 must be generic enough that Clients and Projects are just specialized databases, not one-off tables

- Editor custom blocks API (used for business blocks later) should be sketched in Week 6 even if not exposed

# 9. Final Notes

This plan is a reasonable starting point, not a contract. Your actual experience building Month 1 will teach you things that change Month 2 estimates. Update this document weekly based on what you learn. The worst thing you can do is stick to a plan that's become wrong; the second worst is throw it out entirely.

Phase 1 will feel like it's going slow. Auth and infrastructure always do. Stay disciplined. The payoff is that Phase 2-5 go much faster because the foundation is clean. Skimp on Phase 1 and every subsequent phase becomes harder.

When Week 8 arrives and you have the working demo, share it publicly. Foundation is invisible to users but visible to other developers — their attention will compound into your launch audience.

Now stop reading and start shipping.